## Dashboard
PROJECT IRONBEND
Deal Process Tracker ¦ Northline Precision Pipe Bending & Fabrication Ltd.
|  |  |  | Report date: |  |  | 2026-08-10
BUYERS IN UNIVERSE |  | NDAs SIGNED |  | CIMs SENT |  | IOIs RECEIVED |  | MGMT MEETINGS HELD
138 |  | 70 |  | 70 |  | 23 |  | 13
Newly sourced from buyer-universe research — not yet contacted: |  |  |  |  | 16 buyers |  | See Buyer Universe tab →
DEAL FUNNEL — BUYERS REACHING EACH STAGE (LIVE, LINKED TO BUYER TRACKER)
1. Teaser | 2. NDA | 3. CIM Sent | 4. IOI Received | 5. Mgmt Meeting | 6. LOI Signed | 7. Diligence | 8. Definitive Agmt | 9. Close
122 | 70 | 70 | 23 | 13 | 1 | 1 | 0 | 0
buyers | 57.38% | 100% | 32.86% | 56.52% | 7.692% | 100% | 0% | 0%
PIPELINE STATUS (LIVE)
Active (incl. Exclusivity) |  | 1 | Declined / Passed |  | 93 | Not Contacted / No Resp. / On Hold |  | 44
INDICATIVE VALUATION RANGE FROM IOIs RECEIVED (LIVE)
Low ($mm) |  | 7 | Average ($mm) |  | 10.6587 | High ($mm) |  | 13.7
OVERALL DEAL MILESTONE TIMELINE — PROJECT IRONBEND
# | Milestone |  |  | Target Date | Actual Date | Status
1 | Teaser |  |  | 2026-03-02 | 2026-03-02 | Complete
2 | NDA |  |  | 2026-03-16 | 2026-03-25 | Complete
3 | CIM Sent |  |  | 2026-04-15 | 2026-04-15 | Complete
4 | IOI Received |  |  | 2026-06-15 | 2026-06-18 | Complete
5 | Management Meeting |  |  | 2026-07-15 | 2026-07-18 | Complete
6 | LOI Signed |  |  | 2026-07-20 | 2026-07-21 | Complete
7 | Diligence Checklist |  |  | 2026-09-11 | — | In Progress
8 | Definitive Agreement |  |  | 2026-09-18 | — | Not Started
9 | Close |  |  | 2026-10-31 | — | Not Started
Current stage: 7 — Diligence (in progress, 9 of 26 items complete). Lead buyer B001 under 60-day exclusivity from 21-Jul-2026 (to 19-Sep-2026); definitive agreement targeted 18-Sep-2026, close 31-Oct-2026.
This dashboard is fully linked to the Buyer Tracker tab — funnel counts, status mix, IOI range and the current-stage line recalculate automatically as tracker rows are updated. Manual inputs: the report date (top right) and the milestone table (Target/Actual Date, Status). See the Instructions tab.
VISUAL SUMMARY — LIVE CHARTS (LINKED TO BUYER TRACKER)
Chart source data (auto — mirrors the boxes above; do not edit)
Active | 1 |  | Low | 7
Declined / Passed | 93 |  | Average | 10.6587
Not Contacted / Other | 44 |  | High | 13.7

## Buyer Tracker
BUYER TRACKER — PROJECT IRONBEND
138 buyers in universe (122 contacted with the blind teaser + 16 newly sourced, not yet contacted) ¦ Snapshot as of the Dashboard report date ¦ Columns I–T = process dates (edit as milestones occur) ¦ Column V (Current Stage) and W (Days Since Update) calculate automatically — do not edit ¦ Column U (Status) is a dropdown
Buyer ID | Buyer Name | Type | Priority | Primary Contact | Email | Initial Outreach | NDA Sent | 1. Teaser Sent | 2. NDA Signed | 3. CIM Sent | 4. IOI Received | IOI Low ($mm) | IOI High ($mm) | 5. Mgmt Meeting | 6. LOI Signed | 7. Diligence Start | Diligence % | 8. Definitive Agmt | 9. Close Date | Status | Current Stage (auto) | Days Since Update | Notes
B001 | Ridgemont Buyout Partners | Private Equity | B | Mark Choudhury | m.choudhury@ridgemont.com | 2026-03-26 | 2026-03-30 | 2026-03-26 | 2026-04-05 | 2026-04-13 | 2026-05-29 | 11.6 | 13.4 | 2026-07-07 | 2026-07-21 | 2026-07-28 | 34.62% |  |  | Active - Exclusivity | 7 - Diligence | 13 | Selected buyer: LOI countersigned 21-Jul-2026 (60-day exclusivity to 19-Sep-2026); confirmatory diligence since 28-Jul-2026, see Diligence Checklist.
B002 | Wexford Growth Partners | Private Equity | B | Matthew MacAllister | m.macallister@wexford.com | 2026-03-10 | 2026-03-14 | 2026-03-10 | 2026-03-24 | 2026-04-01 | 2026-05-03 | 12.4 | 13.6 | 2026-06-30 | [5 empty] | On Hold | 5 - Mgmt Meeting | 41 | Final-round bidder: submitted a competing LOI on 21-Jul-2026 that was not countersigned (weaker certainty of financing). Backup bidder; on hold during B001 exclusivity.
B003 | Silverpeak Growth Partners | Private Equity | C | Daniel Bergeron | d.bergeron@silverpeak.com | 2026-03-09 | 2026-03-12 | 2026-03-09 | 2026-03-20 | 2026-03-31 | 2026-05-07 | 12 | 12.8 | 2026-07-11 | [5 empty] | On Hold | 5 - Mgmt Meeting | 30 | Final-round bidder after management meeting; did not submit an LOI by the 21-Jul deadline. On hold during B001 exclusivity.
B004 | Cedarbrook Growth Partners | Family Office | B | Thomas Osei | t.osei@cedarbrook.com | 2026-03-19 | 2026-03-23 | 2026-03-19 | 2026-03-27 | 2026-04-07 | 2026-05-27 | 9 | 10.2 | 2026-07-16 | [5 empty] | Declined | 5 - Mgmt Meeting | 25 | Declined to proceed after review — cited valuation gap.
B005 | Kestrel Private Equity | Private Equity | A | Michael Nakamura | m.nakamura@kestrel.com | 2026-03-14 | 2026-03-17 | 2026-03-14 | 2026-03-22 | 2026-03-29 | 2026-05-24 | 9 | 10.6 | 2026-07-18 | [5 empty] | Declined | 5 - Mgmt Meeting | 23 | Declined to proceed after review — cited valuation gap.
B006 | Kestrel Industrial Capital | Private Equity | C | Jason Nakamura | j.nakamura@kestrel.com | 2026-03-04 | 2026-03-08 | 2026-03-04 | 2026-03-16 | 2026-03-21 | 2026-06-12 | 13 | 13.7 | 2026-07-13 | [5 empty] | On Hold | 5 - Mgmt Meeting | 28 | Final-round bidder after management meeting; did not submit an LOI by the 21-Jul deadline. On hold during B001 exclusivity.
B007 | Stonegate Metalworks | Strategic | B | Amanda Sorensen | a.sorensen@stonegate.com | 2026-03-16 | 2026-03-20 | 2026-03-16 | 2026-03-23 | 2026-04-03 | 2026-04-23 | 11.3 | 12.3 | 2026-07-01 | [5 empty] | Declined | 5 - Mgmt Meeting | 40 | Declined to proceed after review — cited valuation gap.
B008 | Deerfield Fabrication Group | Strategic | B | Amanda Novak | a.novak@deerfield.com | 2026-03-15 | 2026-03-18 | 2026-03-15 | 2026-03-25 | 2026-04-04 | 2026-06-04 | 7.5 | 8.4 | 2026-07-16 | [5 empty] | On Hold | 5 - Mgmt Meeting | 25 | Final-round bidder after management meeting; did not submit an LOI by the 21-Jul deadline. On hold during B001 exclusivity.
B009 | Larkspur Capital Management | Private Equity | C | Christopher Lindqvist | c.lindqvist@larkspur.com | 2026-03-24 | 2026-03-28 | 2026-03-24 | 2026-04-07 | 2026-04-10 | 2026-05-15 | 10.5 | 12.2 | 2026-07-06 | [5 empty] | Declined | 5 - Mgmt Meeting | 35 | Declined to proceed after review — cited valuation gap.
B010 | Highfield Equity Partners | Family Office | C | James Okafor | j.okafor@highfield.com | 2026-03-20 | 2026-03-24 | 2026-03-20 | 2026-03-27 | 2026-04-01 | 2026-05-19 | 8.1 | 8.9 | 2026-06-23 | [5 empty] | Declined | 5 - Mgmt Meeting | 48 | Declined to proceed after review — cited valuation gap.
B011 | Ironwood Steel Works | Strategic | A | Christopher MacAllister | c.macallister@ironwood.com | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-20 | 2026-03-28 | 2026-05-14 | 7.8 | 9 | 2026-07-03 | [5 empty] | Declined | 5 - Mgmt Meeting | 38 | Declined to proceed after review — cited valuation gap.
B012 | Northbridge Investment Partners | Private Equity | B | Rachel Delacroix | r.delacroix@northbridge.com | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-27 | 2026-04-02 | 2026-05-23 | 12.7 | 13.3 | 2026-07-14 | [5 empty] | Declined | 5 - Mgmt Meeting | 27 | Declined to proceed after review — cited valuation gap.
B013 | Blackstone Falls Energy Services | Strategic | C | Stephanie Whitcombe | s.whitcombe@blackstone.com | 2026-03-27 | 2026-03-31 | 2026-03-27 | 2026-04-06 | 2026-04-10 | 2026-05-29 | 12.2 | 13.6 | 2026-07-02 | [5 empty] | Declined | 5 - Mgmt Meeting | 39 | Declined to proceed after review — cited valuation gap.
B014 | Amberline Capital Partners | Family Office | B | Megan Lindqvist | m.lindqvist@amberline.com | 2026-03-09 | 2026-03-12 | 2026-03-09 | 2026-03-23 | 2026-04-01 | 2026-06-04 | 8.2 | 9.8 | [6 empty] | Declined | 4 - IOI Received | 67 | Declined to proceed after review — cited valuation gap.
B015 | Copperfield Manufacturing Corp. | Strategic | B | Thomas Sorensen | t.sorensen@copperfield.com | 2026-03-14 | 2026-03-18 | 2026-03-14 | 2026-03-27 | 2026-04-01 | 2026-05-15 | 10.3 | 11.5 | [6 empty] | On Hold | 4 - IOI Received | 87 | IOI received but not advanced to management meetings (lower or less certain bid). Held in reserve during exclusivity.
B016 | Chandler Partners LLC | Private Equity | C | Andrew Bianchi | a.bianchi@chandler.com | 2026-03-14 | 2026-03-18 | 2026-03-14 | 2026-03-24 | 2026-03-26 | 2026-06-17 | 11.7 | 13.3 | [6 empty] | On Hold | 4 - IOI Received | 54 | IOI received but not advanced to management meetings (lower or less certain bid). Held in reserve during exclusivity.
B017 | Larkspur Capital Group | Private Equity | C | Danielle Fontaine | d.fontaine@larkspur.com | 2026-03-06 | 2026-03-09 | 2026-03-06 | 2026-03-14 | 2026-03-21 | 2026-05-12 | 10.9 | 12.3 | [6 empty] | On Hold | 4 - IOI Received | 90 | IOI received but not advanced to management meetings (lower or less certain bid). Held in reserve during exclusivity.
B018 | Fieldstone Private Equity | Private Equity | A | Megan Kowalski | m.kowalski@fieldstone.com | 2026-03-14 | 2026-03-15 | 2026-03-14 | 2026-03-27 | 2026-03-31 | 2026-05-09 | 11.9 | 12.4 | [6 empty] | Declined | 4 - IOI Received | 93 | Declined to proceed after review — cited valuation gap.
B019 | Ironwood Process Equipment | Strategic | C | Brian Ferris | b.ferris@ironwood.com | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-03-09 | 2026-03-17 | 2026-05-29 | 8.2 | 8.9 | [6 empty] | Declined | 4 - IOI Received | 73 | Declined to proceed after review — cited valuation gap.
B020 | Harrow Investment Partners | Private Equity | A | Kevin Sorensen | k.sorensen@harrow.com | 2026-03-16 | 2026-03-19 | 2026-03-16 | 2026-03-29 | 2026-04-06 | 2026-06-18 | 7.7 | 9.3 | [6 empty] | On Hold | 4 - IOI Received | 53 | IOI received but not advanced to management meetings (lower or less certain bid). Held in reserve during exclusivity.
B021 | Cobalt Private Equity | Private Equity | B | Laura Novak | l.novak@cobalt.com | 2026-03-12 | 2026-03-15 | 2026-03-12 | 2026-03-22 | 2026-03-31 | 2026-04-24 | 7.4 | 9.2 | [6 empty] | On Hold | 4 - IOI Received | 108 | IOI received but not advanced to management meetings (lower or less certain bid). Held in reserve during exclusivity.
B022 | Marlow Fund IV LP | Family Office | B | Robert Beaudry | r.beaudry@marlow.com | 2026-03-26 | 2026-03-30 | 2026-03-26 | 2026-04-09 | 2026-04-13 | 2026-05-28 | 7 | 8.2 | [6 empty] | Declined | 4 - IOI Received | 74 | Declined to proceed after review — cited valuation gap.
B023 | Highland Fabrication Group | Strategic | B | Steven Reinholt | s.reinholt@highland.com | 2026-03-15 | 2026-03-18 | 2026-03-15 | 2026-03-29 | 2026-04-06 | 2026-05-02 | 10.9 | 12.1 | [6 empty] | On Hold | 4 - IOI Received | 100 | IOI received but not advanced to management meetings (lower or less certain bid). Held in reserve during exclusivity.
B024 | Silverpeak Fund IV LP | Private Equity | A | Thomas Vasquez | t.vasquez@silverpeak.com | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-16 | 2026-03-19 | [9 empty] | Passed | 3 - CIM Sent | 144 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B025 | Wexford Partners LLC | Private Equity | A | Danielle Kowalski | d.kowalski@wexford.com | 2026-03-13 | 2026-03-17 | 2026-03-13 | 2026-03-23 | 2026-04-02 | [9 empty] | Passed | 3 - CIM Sent | 130 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B026 | Deerpath Growth Partners | Private Equity | A | Emily Choudhury | e.choudhury@deerpath.com | 2026-03-22 | 2026-03-23 | 2026-03-22 | 2026-03-25 | 2026-04-04 | [9 empty] | Passed | 3 - CIM Sent | 128 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B027 | Palisade Buyout Partners | Private Equity | A | Sarah Delacroix | s.delacroix@palisade.com | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-21 | 2026-03-29 | [9 empty] | Passed | 3 - CIM Sent | 134 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B028 | Sable Point Partners LLC | Private Equity | A | Robert Vasquez | r.vasquez@sable.com | 2026-03-06 | 2026-03-10 | 2026-03-06 | 2026-03-21 | 2026-03-27 | [9 empty] | Passed | 3 - CIM Sent | 136 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B029 | Crestview Pressure Systems | Strategic | B | Emily Nakamura | e.nakamura@crestview.com | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-15 | 2026-03-25 | [9 empty] | Passed | 3 - CIM Sent | 138 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B030 | Cascade Process Equipment | Strategic | B | Brian Sinclair | b.sinclair@cascade.com | 2026-03-10 | 2026-03-13 | 2026-03-10 | 2026-03-15 | 2026-03-24 | [9 empty] | Passed | 3 - CIM Sent | 139 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B031 | Whitecliff Piping Solutions | Strategic | A | Ryan Callahan | r.callahan@whitecliff.com | 2026-03-21 | 2026-03-25 | 2026-03-21 | 2026-03-30 | 2026-04-03 | [9 empty] | Passed | 3 - CIM Sent | 129 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B032 | Chandler Industrial Capital | Private Equity | A | Danielle Renard | d.renard@chandler.com | 2026-03-07 | 2026-03-10 | 2026-03-07 | 2026-03-20 | 2026-03-29 | [9 empty] | Passed | 3 - CIM Sent | 134 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B033 | Millbrook Energy Services | Strategic | B | Rachel Talbot | r.talbot@millbrook.com | 2026-03-11 | 2026-03-14 | 2026-03-11 | 2026-03-19 | 2026-03-28 | [9 empty] | Passed | 3 - CIM Sent | 135 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B034 | Wexford Capital Partners | Family Office | C | Brian Bianchi | b.bianchi@wexford.com | 2026-03-14 | 2026-03-16 | 2026-03-14 | 2026-03-28 | 2026-04-01 | [9 empty] | Passed | 3 - CIM Sent | 131 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B035 | Whitecliff Energy Infrastructure | Strategic | A | Christopher Renard | c.renard@whitecliff.com | 2026-03-20 | 2026-03-23 | 2026-03-20 | 2026-03-28 | 2026-04-02 | [9 empty] | Passed | 3 - CIM Sent | 130 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B036 | Thornfield Capital Group | Private Equity | B | Jason Vasquez | j.vasquez@thornfield.com | 2026-03-05 | 2026-03-07 | 2026-03-05 | 2026-03-18 | 2026-03-23 | [9 empty] | Passed | 3 - CIM Sent | 140 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B037 | Crestview Fabrication Group | Strategic | B | Jason Delacroix | j.delacroix@crestview.com | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-04-05 | 2026-04-11 | [9 empty] | Passed | 3 - CIM Sent | 121 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B038 | Highland Industrial Holdings | Strategic | A | Megan Harmon | m.harmon@highland.com | 2026-03-20 | 2026-03-22 | 2026-03-20 | 2026-03-26 | 2026-04-03 | [9 empty] | Passed | 3 - CIM Sent | 129 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B039 | Harrow Fund IV LP | Private Equity | B | Christine Novak | c.novak@harrow.com | 2026-03-15 | 2026-03-16 | 2026-03-15 | 2026-03-28 | 2026-04-01 | [9 empty] | Passed | 3 - CIM Sent | 131 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B040 | Highfield Industrial Partners | Private Equity | A | Ashley Callahan | a.callahan@highfield.com | 2026-03-22 | 2026-03-24 | 2026-03-22 | 2026-04-04 | 2026-04-07 | [9 empty] | Passed | 3 - CIM Sent | 125 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B041 | Sagebrush Industrial Partners | Private Equity | C | Andrew Whitfield | a.whitfield@sagebrush.com | 2026-03-17 | 2026-03-18 | 2026-03-17 | 2026-03-22 | 2026-04-01 | [9 empty] | Passed | 3 - CIM Sent | 131 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B042 | Silverline Energy Infrastructure | Strategic | C | Jennifer Sorensen | j.sorensen@silverline.com | 2026-03-22 | 2026-03-23 | 2026-03-22 | 2026-04-01 | 2026-04-09 | [9 empty] | Passed | 3 - CIM Sent | 123 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B043 | Osprey Investment Partners | Private Equity | B | Steven Vasquez | s.vasquez@osprey.com | 2026-03-06 | 2026-03-07 | 2026-03-06 | 2026-03-16 | 2026-03-23 | [9 empty] | Passed | 3 - CIM Sent | 140 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B044 | Aldergate Capital Management | Private Equity | C | Amanda Fontaine | a.fontaine@aldergate.com | 2026-03-22 | 2026-03-23 | 2026-03-22 | 2026-04-04 | 2026-04-12 | [9 empty] | Passed | 3 - CIM Sent | 120 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B045 | Amberline Private Equity | Private Equity | C | Thomas Langille | t.langille@amberline.com | 2026-03-19 | 2026-03-20 | 2026-03-19 | 2026-03-22 | 2026-03-31 | [9 empty] | Passed | 3 - CIM Sent | 132 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B046 | Bedrock Manufacturing Corp. | Strategic | B | Ryan MacAllister | r.macallister@bedrock.com | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-04-04 | 2026-04-15 | [9 empty] | Passed | 3 - CIM Sent | 117 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B047 | Kestrel Industrial Partners | Private Equity | B | Brian Duquette | b.duquette@kestrel.com | 2026-03-09 | 2026-03-10 | 2026-03-09 | 2026-03-17 | 2026-03-23 | [9 empty] | Passed | 3 - CIM Sent | 140 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B048 | Sable Point Growth Partners | Private Equity | B | Mark Bergeron | m.bergeron@sable.com | 2026-03-16 | 2026-03-19 | 2026-03-16 | 2026-03-30 | 2026-04-11 | [9 empty] | Passed | 3 - CIM Sent | 121 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B049 | Whitecliff Energy Services | Strategic | B | Emily Delacroix | e.delacroix@whitecliff.com | 2026-03-21 | 2026-03-25 | 2026-03-21 | 2026-04-05 | 2026-04-13 | [9 empty] | Passed | 3 - CIM Sent | 119 | Reviewed CIM; passed before IOIs (not a strategic fit at this time).
B050 | Lakeshore Fabricators Inc. | Strategic | B | Ashley Reinholt | a.reinholt@lakeshore.com | 2026-03-17 | 2026-03-21 | 2026-03-17 | 2026-03-24 | 2026-03-29 | [9 empty] | Passed | 3 - CIM Sent | 134 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B051 | Larkspur Industrial Partners | Private Equity | A | Samantha Osei | s.osei@larkspur.com | 2026-03-08 | 2026-03-10 | 2026-03-08 | 2026-03-18 | 2026-03-19 | [9 empty] | Passed | 3 - CIM Sent | 144 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B052 | Ironwood Fabricators Inc. | Strategic | B | Nicole Harmon | n.harmon@ironwood.com | 2026-03-10 | 2026-03-12 | 2026-03-10 | 2026-03-20 | 2026-03-21 | [9 empty] | Passed | 3 - CIM Sent | 142 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B053 | Ironbridge Capital Group | Private Equity | C | Steven Langille | s.langille@ironbridge.com | 2026-03-10 | 2026-03-14 | 2026-03-10 | 2026-03-22 | 2026-03-23 | [9 empty] | Passed | 3 - CIM Sent | 140 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B054 | Sterling Metalworks | Strategic | B | Stephanie Whitfield | s.whitfield@sterling.com | 2026-03-08 | 2026-03-09 | 2026-03-08 | 2026-03-16 | 2026-03-17 | [9 empty] | Passed | 3 - CIM Sent | 146 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B055 | Blackstone Falls Metalworks | Strategic | C | Michael Pearson | m.pearson@blackstone.com | 2026-03-17 | 2026-03-20 | 2026-03-17 | 2026-04-01 | 2026-04-02 | [9 empty] | Passed | 3 - CIM Sent | 130 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B056 | Keystone Manufacturing Corp. | Strategic | B | Stephanie Delacroix | s.delacroix@keystone.com | 2026-03-17 | 2026-03-20 | 2026-03-17 | 2026-03-24 | 2026-03-26 | [9 empty] | Passed | 3 - CIM Sent | 137 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B057 | Foothills Industrial Group | Strategic | B | Kevin Renard | k.renard@foothills.com | 2026-03-27 | 2026-03-31 | 2026-03-27 | 2026-04-03 | 2026-04-03 | [9 empty] | Passed | 3 - CIM Sent | 129 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B058 | Wolfpack Energy Infrastructure | Strategic | B | James Bergeron | j.bergeron@wolfpack.com | 2026-03-14 | 2026-03-15 | 2026-03-14 | 2026-03-18 | 2026-03-19 | [9 empty] | Passed | 3 - CIM Sent | 144 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B059 | Concord Capital Partners | Private Equity | B | Jason Pearson | j.pearson@concord.com | 2026-03-20 | 2026-03-21 | 2026-03-20 | 2026-03-28 | 2026-03-28 | [9 empty] | Passed | 3 - CIM Sent | 135 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B060 | Thornfield Partners LLC | Private Equity | B | Nicole MacAllister | n.macallister@thornfield.com | 2026-03-13 | 2026-03-14 | 2026-03-13 | 2026-03-25 | 2026-03-27 | [9 empty] | Passed | 3 - CIM Sent | 136 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B061 | Ironbridge Partners LLC | Private Equity | B | Amanda Whitcombe | a.whitcombe@ironbridge.com | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-28 | 2026-03-28 | [9 empty] | Passed | 3 - CIM Sent | 135 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B062 | Thornfield Holdings | Private Equity | B | Jason Beaudry | j.beaudry@thornfield.com | 2026-03-10 | 2026-03-14 | 2026-03-10 | 2026-03-21 | 2026-03-23 | [9 empty] | Passed | 3 - CIM Sent | 140 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B063 | Fairweather Manufacturing Corp. | Strategic | C | Emily Talbot | e.talbot@fairweather.com | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-18 | 2026-03-19 | [9 empty] | Passed | 3 - CIM Sent | 144 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B064 | Silverpeak Capital Management | Private Equity | B | Jennifer Whitcombe | j.whitcombe@silverpeak.com | 2026-03-26 | 2026-03-29 | 2026-03-26 | 2026-04-05 | 2026-04-05 | [9 empty] | Passed | 3 - CIM Sent | 127 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B065 | Harbor Manufacturing Corp. | Strategic | A | Jason Fontaine | j.fontaine@harbor.com | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-31 | 2026-04-02 | [9 empty] | Passed | 3 - CIM Sent | 130 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B066 | Vantage Energy Services | Strategic | C | Kayla Duquette | k.duquette@vantage.com | 2026-03-26 | 2026-03-30 | 2026-03-26 | 2026-04-04 | 2026-04-04 | [9 empty] | Passed | 3 - CIM Sent | 128 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B067 | Deerpath Private Equity | Private Equity | B | Matthew Langille | m.langille@deerpath.com | 2026-03-05 | 2026-03-08 | 2026-03-05 | 2026-03-18 | 2026-03-20 | [9 empty] | Passed | 3 - CIM Sent | 143 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B068 | Coldstream Manufacturing Corp. | Strategic | B | Mark Sinclair | m.sinclair@coldstream.com | 2026-03-13 | 2026-03-16 | 2026-03-13 | 2026-03-19 | 2026-03-21 | [9 empty] | Passed | 3 - CIM Sent | 142 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B069 | Deerpath Capital Partners | Private Equity | A | Laura Marchand | l.marchand@deerpath.com | 2026-03-19 | 2026-03-22 | 2026-03-19 | 2026-04-02 | 2026-04-04 | [9 empty] | Passed | 3 - CIM Sent | 128 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B070 | Thornfield Industrial Capital | Private Equity | A | David Duquette | d.duquette@thornfield.com | 2026-03-03 | 2026-03-05 | 2026-03-03 | 2026-03-13 | 2026-03-15 | [9 empty] | Passed | 3 - CIM Sent | 148 | Received CIM; did not submit an IOI by the round-1 deadline (18-Jun-2026).
B071 | Wexford Industrial Capital | Family Office | C | Stephanie Marchand | s.marchand@wexford.com | 2026-03-06 | 2026-03-07 | 2026-03-06 | [11 empty] | Passed | 1 - Teaser Sent | 156 | Received blind teaser and NDA; NDA not executed (passed on size or sector fit).
B072 | Sable Point Fund IV LP | Private Equity | C | Kevin Okafor | k.okafor@sable.com | 2026-03-05 | 2026-03-08 | 2026-03-05 | [11 empty] | Passed | 1 - Teaser Sent | 155 | Reviewed teaser; passed before signing the NDA (not a strategic fit at this time).
B073 | Ironwood Piping Solutions | Strategic | B | Samantha Whitfield | s.whitfield@ironwood.com | 2026-03-17 | 2026-03-20 | 2026-03-17 | [11 empty] | Passed | 1 - Teaser Sent | 143 | Received blind teaser and NDA; NDA not executed (passed on size or sector fit).
B074 | Coldstream Pressure Systems | Strategic | B | Kayla Beaudry | k.beaudry@coldstream.com | 2026-03-03 | 2026-03-06 | 2026-03-03 | [11 empty] | Passed | 1 - Teaser Sent | 157 | Received blind teaser and NDA; NDA not executed (passed on size or sector fit).
B075 | Coldstream Piping Solutions | Strategic | B | Thomas Okafor | t.okafor@coldstream.com | 2026-03-04 | 2026-03-07 | 2026-03-04 | [11 empty] | Passed | 1 - Teaser Sent | 156 | Reviewed teaser; passed before signing the NDA (not a strategic fit at this time).
B076 | Ironclad Industrial Group | Strategic | A | Christopher MacAllister | c.macallister@ironclad.com | 2026-03-22 | 2026-03-24 | 2026-03-22 | [11 empty] | Passed | 1 - Teaser Sent | 139 | Received blind teaser and NDA; NDA not executed (passed on size or sector fit).
B077 | Coldstream Energy Services | Strategic | A | Ashley Novak | a.novak@coldstream.com | 2026-03-27 | 2026-03-31 | 2026-03-27 | [11 empty] | Passed | 1 - Teaser Sent | 132 | Reviewed teaser; passed before signing the NDA (not a strategic fit at this time).
B078 | Deerpath Fund IV LP | Private Equity | A | Brian Marchand | b.marchand@deerpath.com | 2026-03-09 | 2026-03-10 | 2026-03-09 | [11 empty] | Passed | 1 - Teaser Sent | 153 | Reviewed teaser; passed before signing the NDA (not a strategic fit at this time).
B079 | Silverline Industries Ltd. | Strategic | C | Jennifer Kowalski | j.kowalski@silverline.com | 2026-03-21 |  | 2026-03-21 | [11 empty] | No Response | 1 - Teaser Sent | 142 | No response to teaser outreach after two follow-ups.
B080 | Cedarbrook Industrial Partners | Family Office | B | Megan Harmon | m.harmon@cedarbrook.com | 2026-03-26 |  | 2026-03-26 | [11 empty] | Passed | 1 - Teaser Sent | 137 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B081 | Foothills Metalworks | Strategic | B | Matthew Reinholt | m.reinholt@foothills.com | 2026-03-16 |  | 2026-03-16 | [11 empty] | Passed | 1 - Teaser Sent | 147 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B082 | Whitecliff Industries Ltd. | Strategic | B | Rachel Okafor | r.okafor@whitecliff.com | 2026-03-15 |  | 2026-03-15 | [11 empty] | Passed | 1 - Teaser Sent | 148 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B083 | Windrose Investment Partners | Private Equity | B | Rachel Ferris | r.ferris@windrose.com | 2026-03-21 |  | 2026-03-21 | [11 empty] | Passed | 1 - Teaser Sent | 142 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B084 | Cedarbrook Capital Partners | Private Equity | C | Danielle Talbot | d.talbot@cedarbrook.com | 2026-03-08 |  | 2026-03-08 | [11 empty] | Passed | 1 - Teaser Sent | 155 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B085 | Cardinal Point Capital Group | Private Equity | B | Kevin Sinclair | k.sinclair@cardinal.com | 2026-03-04 |  | 2026-03-04 | [11 empty] | No Response | 1 - Teaser Sent | 159 | No response to teaser outreach after two follow-ups.
B086 | Elmwood Capital Management | Private Equity | A | Laura Pearson | l.pearson@elmwood.com | 2026-03-04 |  | 2026-03-04 | [11 empty] | No Response | 1 - Teaser Sent | 159 | No response to teaser outreach after two follow-ups.
B087 | Foothills Steel Works | Strategic | B | Laura Whitfield | l.whitfield@foothills.com | 2026-03-24 |  | 2026-03-24 | [11 empty] | No Response | 1 - Teaser Sent | 139 | No response to teaser outreach after two follow-ups.
B088 | Fieldstone Industrial Capital | Private Equity | B | Megan MacAllister | m.macallister@fieldstone.com | 2026-03-09 |  | 2026-03-09 | [11 empty] | Passed | 1 - Teaser Sent | 154 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B089 | Harrow Capital Partners | Private Equity | B | Rachel Renard | r.renard@harrow.com | 2026-03-16 |  | 2026-03-16 | [11 empty] | No Response | 1 - Teaser Sent | 147 | No response to teaser outreach after two follow-ups.
B090 | Palisade Industrial Partners | Private Equity | B | Michael Bianchi | m.bianchi@palisade.com | 2026-03-10 |  | 2026-03-10 | [11 empty] | Passed | 1 - Teaser Sent | 153 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B091 | Wheatland Fabrication Group | Strategic | B | Christine Harmon | c.harmon@wheatland.com | 2026-03-23 |  | 2026-03-23 | [11 empty] | Passed | 1 - Teaser Sent | 140 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B092 | Broadview Piping Solutions | Strategic | B | Christine Sinclair | c.sinclair@broadview.com | 2026-03-19 |  | 2026-03-19 | [11 empty] | Passed | 1 - Teaser Sent | 144 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B093 | Fieldstone Capital Group | Private Equity | A | Emily Choudhury | e.choudhury@fieldstone.com | 2026-03-10 |  | 2026-03-10 | [11 empty] | Passed | 1 - Teaser Sent | 153 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B094 | Whitecliff Fabricators Inc. | Strategic | A | Mark Nakamura | m.nakamura@whitecliff.com | 2026-03-07 |  | 2026-03-07 | [11 empty] | No Response | 1 - Teaser Sent | 156 | No response to teaser outreach after two follow-ups.
B095 | Millbrook Pressure Systems | Strategic | B | Christine Marchand | c.marchand@millbrook.com | 2026-03-20 |  | 2026-03-20 | [11 empty] | Passed | 1 - Teaser Sent | 143 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B096 | Cedarbrook Industrial Capital | Private Equity | B | Julia Marchand | j.marchand@cedarbrook.com | 2026-03-16 |  | 2026-03-16 | [11 empty] | Passed | 1 - Teaser Sent | 147 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B097 | Ironclad Energy Services | Strategic | C | Jason Marchand | j.marchand@ironclad.com | 2026-03-10 |  | 2026-03-10 | [11 empty] | No Response | 1 - Teaser Sent | 153 | No response to teaser outreach after two follow-ups.
B098 | Ironbridge Growth Partners | Family Office | B | Matthew Kowalski | m.kowalski@ironbridge.com | 2026-03-04 |  | 2026-03-04 | [11 empty] | Passed | 1 - Teaser Sent | 159 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B099 | Marlin Bay Investment Partners | Private Equity | C | Megan Novak | m.novak@marlin.com | 2026-03-25 |  | 2026-03-25 | [11 empty] | Passed | 1 - Teaser Sent | 138 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B100 | Foothills Process Equipment | Strategic | B | Andrew Langille | a.langille@foothills.com | 2026-03-04 |  | 2026-03-04 | [11 empty] | No Response | 1 - Teaser Sent | 159 | No response to teaser outreach after two follow-ups.
B101 | Cedarbrook Buyout Partners | Private Equity | C | Emily Bianchi | e.bianchi@cedarbrook.com | 2026-03-20 |  | 2026-03-20 | [11 empty] | No Response | 1 - Teaser Sent | 143 | No response to teaser outreach after two follow-ups.
B102 | Talus Industrial Partners | Family Office | C | Brian Whitfield | b.whitfield@talus.com | 2026-03-23 |  | 2026-03-23 | [11 empty] | No Response | 1 - Teaser Sent | 140 | No response to teaser outreach after two follow-ups.
B103 | Northbridge Capital Management | Private Equity | B | Mark Duquette | m.duquette@northbridge.com | 2026-03-26 |  | 2026-03-26 | [11 empty] | Passed | 1 - Teaser Sent | 137 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B104 | Northbridge Private Equity | Private Equity | B | Ryan Fontaine | r.fontaine@northbridge.com | 2026-03-22 |  | 2026-03-22 | [11 empty] | Passed | 1 - Teaser Sent | 141 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B105 | Palisade Holdings | Private Equity | A | Daniel Duquette | d.duquette@palisade.com | 2026-03-20 |  | 2026-03-20 | [11 empty] | No Response | 1 - Teaser Sent | 143 | No response to teaser outreach after two follow-ups.
B106 | Amberline Capital Management | Private Equity | C | Amanda Choudhury | a.choudhury@amberline.com | 2026-03-04 |  | 2026-03-04 | [11 empty] | Passed | 1 - Teaser Sent | 159 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B107 | Trailhead Energy Services | Strategic | B | Kayla Callahan | k.callahan@trailhead.com | 2026-03-12 |  | 2026-03-12 | [11 empty] | Passed | 1 - Teaser Sent | 151 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B108 | Cascade Industrial Group | Strategic | C | Ashley Talbot | a.talbot@cascade.com | 2026-03-12 |  | 2026-03-12 | [11 empty] | No Response | 1 - Teaser Sent | 151 | No response to teaser outreach after two follow-ups.
B109 | Vireo Growth Partners | Private Equity | B | Amanda Renard | a.renard@vireo.com | 2026-03-23 |  | 2026-03-23 | [11 empty] | No Response | 1 - Teaser Sent | 140 | No response to teaser outreach after two follow-ups.
B110 | Fieldstone Investment Partners | Private Equity | C | Christopher Vasquez | c.vasquez@fieldstone.com | 2026-03-03 |  | 2026-03-03 | [11 empty] | No Response | 1 - Teaser Sent | 160 | No response to teaser outreach after two follow-ups.
B111 | Crestview Industries Ltd. | Strategic | B | Daniel Bergeron | d.bergeron@crestview.com | 2026-03-12 |  | 2026-03-12 | [11 empty] | Passed | 1 - Teaser Sent | 151 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B112 | Union Pacific West Industrial Holdings | Strategic | B | Jennifer Delacroix | j.delacroix@union.com | 2026-03-18 |  | 2026-03-18 | [11 empty] | Passed | 1 - Teaser Sent | 145 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B113 | Continental Pressure Systems | Strategic | C | Mark Whitfield | m.whitfield@continental.com | 2026-03-19 |  | 2026-03-19 | [11 empty] | Passed | 1 - Teaser Sent | 144 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B114 | Talus Private Equity | Private Equity | A | Daniel Sorensen | d.sorensen@talus.com | 2026-03-18 |  | 2026-03-18 | [11 empty] | Passed | 1 - Teaser Sent | 145 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B115 | Deerpath Industrial Partners | Private Equity | C | Nicole Langille | n.langille@deerpath.com | 2026-03-22 |  | 2026-03-22 | [11 empty] | Passed | 1 - Teaser Sent | 141 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B116 | Harrow Capital Group | Private Equity | A | Daniel Delacroix | d.delacroix@harrow.com | 2026-03-10 |  | 2026-03-10 | [11 empty] | No Response | 1 - Teaser Sent | 153 | No response to teaser outreach after two follow-ups.
B117 | Ashford Equity Partners | Private Equity | C | Stephanie Nakamura | s.nakamura@ashford.com | 2026-03-16 |  | 2026-03-16 | [11 empty] | Passed | 1 - Teaser Sent | 147 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B118 | Harbor Pressure Systems | Strategic | B | Steven Renard | s.renard@harbor.com | 2026-03-02 |  | 2026-03-02 | [11 empty] | No Response | 1 - Teaser Sent | 161 | No response to teaser outreach after two follow-ups.
B119 | Marlin Bay Industrial Capital | Private Equity | C | Kevin Langille | k.langille@marlin.com | 2026-03-24 |  | 2026-03-24 | [11 empty] | No Response | 1 - Teaser Sent | 139 | No response to teaser outreach after two follow-ups.
B120 | Continental Piping Solutions | Strategic | B | Laura Marchand | l.marchand@continental.com | 2026-03-19 |  | 2026-03-19 | [11 empty] | Passed | 1 - Teaser Sent | 144 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B121 | Greystone Industrial Capital | Private Equity | B | Amanda Bergeron | a.bergeron@greystone.com | 2026-03-05 |  | 2026-03-05 | [11 empty] | Passed | 1 - Teaser Sent | 158 | Received blind teaser; did not sign the NDA (passed on size or sector fit).
B122 | Lakeshore Fabrication Group | Strategic | B | Daniel Talbot | d.talbot@lakeshore.com | 2026-03-06 |  | 2026-03-06 | [11 empty] | No Response | 1 - Teaser Sent | 157 | No response to teaser outreach after two follow-ups.
B123 | CESSCO Fabrication & Engineering Ltd. | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Nisku, AB — Direct regional competitor (ASME/ABSA certified). Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B124 | Alberta Custom Pipe Bending & Mfg. (2010) Ltd. | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Edmonton, AB — Direct same-city competitor, near-identical certification. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B125 | Bri-Steel Manufacturing (Integris International Inc.) | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Edmonton, AB — Seamless pipe mfr.; vertical extension into bending/vessels. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B126 | JNE Welding | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Saskatoon, SK — Large regional pressure vessel fabricator. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B127 | Moss Fabrication Ltd. | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Calgary, AB — Smaller Calgary fabricator; would gain code-stamp via acquisition. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B128 | Matrix Service Company | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Tulsa, OK (NASDAQ: MTRX) — Public EPC/fabrication co.; serial acquirer of small fabricators. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B129 | Total Energy Services Inc. | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Calgary, AB (TSX: TOT) — Public energy services co. with fabrication segment. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B130 | DXP Enterprises, Inc. | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Houston, TX (NASDAQ: DXPE) — Public roll-up; disclosed comparable Calgary deal (Mequipco). Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B131 | Enerflex Ltd. | Strategic | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Calgary, AB (TSX/NYSE: EFXT) — Public compression/process equipment manufacturer. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B132 | Clairvest Group Inc. | Private Equity | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Toronto, ON (TSX: CVG) — Listed PE firm w/ stated oilfield services mandate. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B133 | CORE Industrial Partners | Private Equity | A | [16 empty] | Not Contacted | 0 - Not Contacted | - | Chicago, IL — LMM manufacturing/industrial services specialist PE firm. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B134 | Kinderhook Industries, LLC | Private Equity | B | [16 empty] | Not Contacted | 0 - Not Contacted | - | New York, NY — LMM PE firm; check size likely above target scale. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B135 | Wynnchurch Capital, L.P. | Private Equity | B | [16 empty] | Not Contacted | 0 - Not Contacted | - | Rosemont, IL — MM industrial PE w/ Canadian affiliate; sizing likely a stretch. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B136 | Industrial Opportunity Partners (IOP) | Private Equity | B | [16 empty] | Not Contacted | 0 - Not Contacted | - | Evanston, IL — MM manufacturing PE; check size likely above target scale. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B137 | American Industrial Partners | Private Equity | B | [16 empty] | Not Contacted | 0 - Not Contacted | - | New York, NY — Large industrial PE; platform minimum >$500mm revenue. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.
B138 | Birch Hill Equity Partners | Private Equity | B | [16 empty] | Not Contacted | 0 - Not Contacted | - | Toronto, ON — Canadian generalist PE; deal-size floor above target. Not yet contacted. See Buyer Universe tab for full rationale, check size & sources.

## Buyer Universe
BUYER UNIVERSE / TARGET LIST — PROJECT IRONBEND
Real, named strategic and financial buyers screened for Northline Precision Pipe Bending & Fabrication Ltd. (ASME 'U'-Stamp / National Board certified pipe bending & pressure vessel fabricator, Edmonton, AB; ~$9.4mm 2025E revenue). Compiled from public company filings, press releases, and firm websites — see Source column. Not an exhaustive list.
# | Buyer Name | Type | HQ / Region | Public / Private | Rationale / Strategic Fit | Est. Check Size / Capacity | Prior Relevant Acquisitions | Source
STRATEGIC BUYERS
1 | CESSCO Fabrication & Engineering Ltd. | Strategic | Nisku, AB | Private | Direct regional competitor. ~75-year-old Alberta pressure vessel fabricator with multiple ASME and ABSA certifications, serving the same oil & gas / petrochemical / mining customer base in Western Canada's high-load corridor. Acquisition would consolidate certified fabrication capacity and backlog in-region. | Not publicly disclosed (privately held; no PE sponsor identified). | None identified in public sources. | cessco.ca
2 | Alberta Custom Pipe Bending & Mfg. (2010) Ltd. | Strategic | Edmonton, AB | Private | Near-identical certification and service profile to the Company — ASME and National Board certified fabricator in the same Edmonton industrial corridor. A direct, same-city competitor; combination would remove a head-to-head bidder on certified pipe bending / pressure vessel work and add capacity. | Not publicly disclosed (privately held). | None identified in public sources. | acpbm.com
3 | Bri-Steel Manufacturing (Integris International Inc.) | Strategic | Edmonton, AB | Private | Edmonton-based large-diameter seamless steel pipe manufacturer (NPS 12-36") serving oil & gas, pipeline and infrastructure customers; API/ASME/CSA certified. Adding Northline's bending and pressure vessel capability would let Bri-Steel offer fabricated/bent pipe products alongside its mill output — a logical vertical extension for an already-acquisitive, expansion-minded manufacturer. | ~US$23.4mm 2025 revenue (Bri-Steel); scale suggests capacity for a bolt-on of this size, but not publicly confirmed. | Acquired the former GEFCO facility (Enid, OK) to build a second Thermal Pipe Expansion mill (asset purchase, not a company acquisition). | ZoomInfo; manufacturinginfocus.com; bri-steel.com
4 | JNE Welding | Strategic | Saskatoon, SK | Private | One of Saskatchewan's largest full-service pressure vessel fabricators (77,000 sq ft shop, vessels up to 250 tons), serving oil sands, mining and potash customers. Geographic and end-market adjacency to Northline with limited certified-fabrication overlap — a bolt-on would extend JNE's footprint into Alberta's oil & gas base. | Not publicly disclosed (privately held). | None identified in public sources. | jnewelding.com
5 | Moss Fabrication Ltd. | Strategic | Calgary, AB | Private | Calgary-based fabricator of pressure vessels, separators and skid packages for Western Canadian gas and oilfields since 1983, CSA/API/ASME compliant. Smaller regional player for whom acquiring Northline's ASME 'U'-Stamp and National Board dual certification would be a fast route to code-stamped pressure vessel work it cannot currently bid without third-party certification. | Not publicly disclosed (privately held). | None identified in public sources. | mossfabrication.ca
6 | Matrix Service Company | Strategic | Tulsa, OK (NASDAQ: MTRX) | Public | Public EPC and fabrication company for aboveground storage tanks, terminals and ASME pressure vessels, with existing U.S. and Canadian operations. A serial acquirer of smaller fabrication and piping businesses historically; Northline's certified capacity and Tier-1 O&G relationships would extend Matrix's Storage and Terminal Solutions / Process and Industrial Facilities segments into Western Canada. | Public company; funds bolt-ons from cash + credit facility. Comparable historical deal was <US$10mm (2014 upstream contractor acquisition). | San Luis Piping Construction & West Coast Industrial Coatings (~US$10.2mm, 1991); Health Engineering, Sarnia ON (1993); PDM Engineering; Houston Interests/River Consulting group (2016); Baillie Tank Equipment (2016); an upstream contractor for <US$10mm (2014). | matrixservicecompany.com; PitchBook; investors.matrixservicecompany.com
7 | Total Energy Services Inc. | Strategic | Calgary, AB (TSX: TOT) | Public | Public, Calgary-based diversified energy services company whose Compression and Process Services segment (Bidell Gas Compression / process equipment fabrication) is the majority revenue driver. Explicit 'disciplined acquisition strategy' for fabrication and process equipment businesses — Northline's ASME/NB certification would add pressure vessel capability alongside Total's existing compression fabrication. | Public company (TSX: TOT); stock ~C$19/share as of mid-2026. Deal sizing not disclosed for fabrication bolt-ons specifically. | Multiple acquisitions incl. Savanna Energy Services merger (2017, drilling); Korea National Oil asset purchase (2025). | totalenergy.ca; PitchBook; SEC filings
8 | DXP Enterprises, Inc. | Strategic | Houston, TX (NASDAQ: DXPE) | Public | Public industrial MROP distributor operating an explicit, disclosed roll-up model (17+ acquisitions since 2004) with a demonstrated pattern of small Western Canadian bolt-ons at revenue scale directly comparable to Northline. Certified fabrication capability would be a natural adjacent-service addition to DXP's existing Alberta operations. | Directly comparable disclosed deals: Mequipco Ltd. (Calgary, ~CAD$9.9mm revenue, 2026) and Industrial Paramedic Services (Calgary/Nisku, ~US$21mm revenue / ~US$4mm EBITDA, 2012) — both funded with cash + stock. | Industrial Paramedic Services, Calgary/Nisku (2012); Mequipco Ltd., Calgary (2026); 15+ other bolt-ons since 2004 (Delta Process Equipment, Precision Industries, Rocky Mtn. Supply, PFI, others). | SEC 8-K filings; investing.com; ir.dxpe.com
9 | Enerflex Ltd. | Strategic | Calgary, AB (TSX/NYSE: EFXT) | Public | Public Calgary-based manufacturer of natural gas compression and process equipment with an active M&A program. Adjacent process-equipment fabricator; Northline's pressure vessel and pipe bending capability would complement Enerflex's compression package fabrication and broaden its certified product scope. | Public company (TSX/NYSE: EFXT); deal sizing not disclosed for fabrication-scale bolt-ons. | Absolute Compression Enterprise (2023) and 5 other acquisitions on record. | PitchBook; GlobalData
FINANCIAL BUYERS
10 | Clairvest Group Inc. | Financial | Toronto, ON (TSX: CVG) | Public (PE firm) | Publicly listed Canadian PE firm with an explicitly stated mandate to invest in 'small and mid-sized... oil and gas field services' businesses, among other sectors — one of the few listed sponsors with named oilfield-services intent. Long Toronto/Calgary investor relationships and a consolidation/add-on playbook fit a certification-moat platform like Northline. | ~C$4.6bn capital under management; recent disclosed deals range ~US$30-165mm (e.g., MGM Northfield Park, US$165mm total / US$39mm CVG portion) — likely larger than this target, but smaller platform + add-on strategy possible. | No pipe/pressure-vessel-fabrication acquisition identified specifically; broad oilfield services mandate confirmed on firm website. | clairvest.com; investing.com; ZoomInfo
11 | Kinderhook Industries, LLC | Financial | New York, NY | Private (PE firm) | Lower-middle-market PE firm with 'Environmental & Industrial Services' as one of three named core sectors and 500+ investments/add-ons since 2003. Platform-and-bolt-on model suits a certification-protected niche fabricator; scale is a modest stretch above their typical minimum. | Stated criteria: US$10-50mm equity checks; EV range US$25-150mm — above Northline's $9-13mm indicative range, but a new lower middle-market vehicle (Kinderhook Strategic Opportunities Fund I, $1.1bn, closed 2026) may flex smaller. | No pipe/pressure-vessel-fabrication acquisition identified specifically. | kinderhook.com; Eagle Rock CFO; PR Newswire (KSOF close, Apr 2026)
12 | CORE Industrial Partners | Financial | Chicago, IL | Private (PE firm) | PE firm investing exclusively in lower-middle-market manufacturing, industrial technology and industrial services businesses — sector focus matches a certified fabricator well; explicitly LMM-sized mandate is a closer fit to Northline's scale than most funds on this list. | Firm-level: >US$1.58bn capital commitments; per-deal check size not publicly disclosed. | No pipe/pressure-vessel-fabrication acquisition identified specifically (recent exit: PrecisionX Group, precision machining). | coreipfund.com
13 | Wynnchurch Capital, L.P. | Financial | Rosemont, IL (Canadian affiliate) | Private (PE firm) | Middle-market industrial PE firm with a standing Canadian affiliate and a specific track record of metals and industrial-services roll-ups (aluminum extrusions, MRO field services, critical infrastructure equipment) — the closest sector-and-geography match among the larger funds screened. | ~US$9.2bn regulatory AUM; recent disclosed deal sizes range widely (e.g., FloWorks sale at ~US$1.6bn EV) — individual platforms are typically larger than this target; most likely fit would be as an add-on to an existing Wynnchurch industrial-services or metals platform. | Astro Shapes (aluminum extrusions); Industrial Service Solutions / ISS (MRO field services); Owen (critical infrastructure equipment); Charter Industries (2025). | wynnchurch.com (news releases)
14 | Industrial Opportunity Partners (IOP) | Financial | Evanston, IL | Private (PE firm) | PE firm focused exclusively on middle-market manufacturing and value-added distribution, with prior acquisitions in two Canadian provinces — demonstrated willingness and infrastructure to close Canadian deals, though its typical target revenue ($50-500mm) is larger than Northline's. | Stated equity check: US$15-100mm per transaction — above Northline's scale; would more likely appear as an add-on sponsor via an existing platform than a standalone bidder. | 30+ platform acquisitions since 2005 (e.g., Viaflex/Raven Engineered Films, N.B. Handy); none identified in pipe/pressure-vessel fabrication specifically. | iopfund.com; Mergr
15 | American Industrial Partners | Financial | New York, NY | Private (PE firm) | Deeply industrial-focused PE firm (Energy Services and Equipment named as a sector of interest) with 125+ platform and add-on acquisitions — sector fit is strong, but included primarily for completeness: their stated minimum platform size is well above Northline's revenue. | ~US$16-17.8bn AUM; platform acquisitions typically require >US$500mm revenue — a clear size mismatch for a US$9.4mm-revenue target; realistic only as a bolt-on to an existing AIP portfolio company, if any overlaps. | 125+ acquisitions across industrial sectors; GD Energy Products (industrial pumps) is the closest sector analog identified. | americanindustrial.com; Mergr; CT Acquisitions directory
16 | Birch Hill Equity Partners | Financial | Toronto, ON | Private (PE firm) | Established Canadian mid-market generalist sponsor (Energy Services and Equipment named as a sector of interest) with a long history of Canadian industrial deals — included for completeness, but its stated deal-size floor is well above this target. | Targets control/significant-minority deals valued C$75mm-$3bn (per Mergr) — roughly 5-10x larger than Northline's indicative $9-13mm EV; a size mismatch unless deployed as an add-on to an existing platform. | 90 M&A transactions on record; none identified in pipe/pressure-vessel fabrication specifically. | birchhillequity.com; Mergr; PitchBook
LEGEND
Green = sector fit AND check size plausibly matches Northline's $9-13mm indicative EV. Yellow = sector fit confirmed, but firm's typical/stated deal size is larger than this target — a realistic bolt-on/add-on candidate rather than a standalone lead bidder.
Research notes: all organizations above are real, named companies verified via public filings, company websites, and news/PE-database sources as of August 2026 (see Source column for each). Fields marked 'not publicly disclosed' reflect genuine gaps in available public data for privately held companies — left blank/noted rather than estimated. This is a screened starting universe (16 names) for further analyst diligence, not an exhaustive or final buyer list; actual check size and appetite would be confirmed through direct buyer-side conversations.

## Diligence Checklist
DILIGENCE CHECKLIST — PROJECT IRONBEND (LEAD BUYER: B001, EXCLUSIVITY)
Stage 7 of the deal process. Update Status and % Complete as items close out — the dashboard summary reads from this tab.
# | Category | Diligence Item | Owner | Status | Target Date | Notes
1 | Financial | Audited financial statements — FY2023-2025 | Advisor / CFO | Complete | 2026-08-01 | Received; reviewed by buyer's QoE team
2 | Financial | Quality of Earnings (QoE) report | Buyer's Accountant | In Progress | 2026-08-20 | Fieldwork underway, on-site this week
3 | Financial | Working capital analysis & target | Advisor / CFO | In Progress | 2026-08-18 | Draft peg schedule circulated
4 | Financial | Backlog and order book schedule | Company | Complete | 2026-08-01 | NPS 6-42 backlog by customer provided
5 | Financial | Customer concentration analysis | Advisor | Complete | 2026-07-30 | Top 5 customers = ~59% of revenue; largest ~18% (matches CIM)
6 | Legal | Corporate structure & cap table review | Buyer's Counsel | Complete | 2026-08-01 | No issues identified
7 | Legal | Material contracts review (MSAs) | Buyer's Counsel | In Progress | 2026-08-22 | Tier-1 operator MSAs under review
8 | Legal | Litigation & claims history | Buyer's Counsel | Complete | 2026-08-05 | No pending litigation
9 | Legal | IP / trade secrets (bending procedures) | Buyer's Counsel | Not Started | 2026-08-25
10 | Regulatory | ASME 'U'-Stamp certification status | Buyer / QA Lead | Complete | 2026-08-03 | Current, next audit Q1 2027
11 | Regulatory | National Board registration status | Buyer / QA Lead | Complete | 2026-08-03 | Current, in good standing
12 | Regulatory | ABSA certification & inspection history | Buyer / QA Lead | In Progress | 2026-08-20 | Requesting 5-yr inspection file
13 | Regulatory | CRN registration schedule (by province) | Buyer / QA Lead | Not Started | 2026-08-25
14 | Commercial | Customer reference calls (top 5) | Buyer / Advisor | In Progress | 2026-08-28 | 3 of 5 calls completed
15 | Commercial | Competitive positioning review | Buyer | Not Started | 2026-09-01
16 | Commercial | Pricing & contract renewal terms | Advisor | In Progress | 2026-08-20 | Reviewing MSA renewal cadence
17 | Operations | Facility & equipment condition assessment | Buyer's Engineer | In Progress | 2026-08-25 | Site visit scheduled Aug 12
18 | Operations | Capacity utilization & throughput analysis | Company | Not Started | 2026-09-01
19 | Operations | Safety & environmental compliance (EHS) | Buyer's Consultant | Not Started | 2026-09-01
20 | Operations | Supplier concentration & raw material sourcing | Company | Complete | 2026-08-05 | Steel supply diversified, 4 mills
21 | HR | Key employee / management retention review | Buyer | In Progress | 2026-08-22 | Retention packages under discussion
22 | HR | Union / labor agreement review | Buyer's Counsel | Complete | 2026-08-05 | Non-union shop confirmed
23 | HR | Compensation & benefits benchmarking | Buyer | Not Started | 2026-09-05
24 | IT | IT systems & cybersecurity assessment | Buyer's IT Consultant | Not Started | 2026-09-05
25 | Tax | Tax structuring & historical filings review | Buyer's Tax Advisor | In Progress | 2026-08-28 | Federal & Alberta filings requested
26 | Insurance | Insurance policy review (property, liability, WCB) | Buyer | Not Started | 2026-09-05
% COMPLETE (AUTO)
Diligence items closed out: |  |  | 9 of 26 items |  | 34.62%

## Instructions
HOW THIS WORKBOOK WORKS
1. STRUCTURE
• Dashboard — the one-pager. Shows the 9-stage deal funnel (Teaser → NDA → CIM → IOI → Management Meeting → LOI → Diligence → Definitive Agreement → Close), pipeline status mix, IOI valuation range, and the overall deal milestone timeline for Project Ironbend. Everything except the report date and the milestone table is a live formula.
• Buyer Tracker — the working tracker. 138 rows pre-loaded: 122 buyers contacted with the blind teaser, plus 16 real buyers freshly sourced from the Buyer Universe tab (Status = Not Contacted, no dates yet). Add new buyers by inserting rows within the table range (row 4 through the last data row) so formulas and formatting copy down automatically.
• Diligence Checklist — detailed checklist for the buyer in exclusivity (26 items across Financial, Legal, Regulatory, Commercial, Operations, HR, IT, Tax and Insurance workstreams), with an auto-calculated % complete.
• Buyer Universe — sourcing reference. 16 real, named strategic and financial buyers researched for this deal (public filings, company sites, press releases), each with rationale/fit, estimated check size, prior relevant acquisitions and a source citation. These are the same 16 buyers appended to the bottom of the Buyer Tracker as "Not Contacted" — update them there once outreach begins.
2. WHAT TO EDIT
Buyer Tracker — edit freely (shown in blue font): columns G-T (process dates), M-N (IOI value range), U (Status dropdown), C (Type dropdown), D (Priority dropdown), X (Notes). Enter a date the moment a milestone happens (e.g. the day an NDA is countersigned goes in column J).
Buyer Tracker — do NOT edit columns V (Current Stage) and W (Days Since Update). These are formulas that read the date columns automatically.
Diligence Checklist — edit Status (dropdown) and Notes as items close out; the % Complete line at the bottom recalculates itself.
Dashboard — only the report date (I6) and the Target Date / Actual Date / Status cells in the 'Overall Deal Milestone Timeline' table are manual. Everything else (KPI strip, funnel, pipeline status, IOI range, current-stage line) is a formula — do not type over it.
3. HOW THE AUTO-UPDATING WORKS
Current Stage (Buyer Tracker, col V): checks each buyer's date columns from Close backward to Teaser Sent and returns the furthest milestone reached — no manual selection needed.
Days Since Update (col W): the Dashboard report date minus the most recent date entered for that buyer — flags stale rows in bold amber automatically if a buyer marked Active hasn't moved in 21+ days. Set the report date to today's date when you update the tracker.
Dashboard funnel counts: each stage box uses COUNT() on the corresponding Buyer Tracker date column (e.g. NDA count = COUNT of non-blank cells in column J), so it always reflects the current state of the tracker.
Dashboard KPIs, status mix, and IOI range: COUNT/COUNTIF/AVERAGE/MIN/MAX formulas referencing the Buyer Tracker range — update instantly as you edit tracker rows.
4. SCALING BEYOND 138 BUYERS
Select the last data row in Buyer Tracker, right-click, Insert Copied Cells (or select the full row and Insert), then fill down columns V and W and the border/zebra formatting from the row above. All Dashboard formulas reference the fixed range B4:X141 by default — if you add rows beyond row 141, extend the ranges in the Dashboard formulas (Find & Replace 141 with your new last row) and re-apply the Buyer Tracker data validations and conditional formatting to the new rows.
5. FORMATTING KEY
Blue text = manual input (safe to edit). Dark grey/black text = formula output (leave alone). Navy header bands mark table headers. Status is shown by text styling rather than colour fills: bold navy = active / in progress, grey = not started or no longer in play, italic grey = no response / on hold. Amber bold in 'Days Since Update' flags an Active buyer with no movement for 21+ days.